## Backlog
Card ID | Card Name | Card URL | Card Description | Refinement State | Priority | Acceptance Criteria Count | Detail in File
670586699b2194988e7359cb | Create Domain Model | https://trello.com/c/LMbb1PcJ/48-create-domain-model | Develop a comprehensive domain model for the application to ensure a clear understanding of the system's structure and relationships between entities. The domain model will serve as the foundation for further development and guide the implementation of features. | Groomed | P1 Next Sprint (yellow) | 5
67058b91dbb68154bf5f7eab | Initialize Backend (Java) | https://trello.com/c/W2YLmzHd/49-initialize-backend-java | Set up the backend environment using Java, including project structure, dependencies, and initial configuration. | Groomed | P1 Next Sprint (yellow) | 5
67058c30b2b5d757365b89f4 | Initialize Database (PostgreSQL) | https://trello.com/c/eShJxl4T/51-initialize-database-postgresql | Set up the PostgreSQL database environment, including schema design and initial configuration. | Groomed | P1 Next Sprint (yellow) | 6
67058be6718361b65b849ef5 | Initialize Frontend (React) | https://trello.com/c/fjAzT1Tx/50-initialize-frontend-react | Set up the frontend environment using React, including project configuration and initial components. | Groomed | P1 Next Sprint (yellow) | 5
67022673b919a061ff880b01 | Contact Landlord Through Listing | https://trello.com/c/2uOBoKNn/37-contact-landlord-through-listing | As a user, I want to be able to contact a landlord by clicking a button on their post. | Groomed | P1 Next Sprint (yellow) | 3
66feee203a4579a108582db3 | Update Account Info | https://trello.com/c/OfhmlU0x/9-update-account-info | As a user, I want to be able to update my account information, such that it is kept accurate and up to date for other users to see. | Groomed | P1 Next Sprint (yellow) | 4 | update_account_info.feature
66fef27a5ad7bb63ba400f17 | Update a Listing | https://trello.com/c/b5xDRLjG/10-update-a-listing | As a user, I want to be able to update an existing listing that I created so that the update will be seen by other users. | Groomed | P1 Next Sprint (yellow) | 2 | update_listing.feature
66fee0a523d39f3e4c541b31 | Create and View Listing | https://trello.com/c/RnIRVSan/3-create-and-view-listing | As a Registered User, I want to be able to create accommodation listings with details such as location, price, and amenities, such that my listing can be seen by other users. | Not Groomed | P1 Next Sprint (yellow) | 4 | create_listing.feature
66fc5209debc2049eee6e301 | Create Account | https://trello.com/c/fRb9QP2q/2-create-account | As a customer, I need to be able to create an account before accessing additional features (posting, sending messages, etc.) on the application. | Groomed | P1 Next Sprint (yellow) | 10 | accounts_functionality.feature
67018efe72fdb8016794bcb1 | View-only Access to Postings Without Registration | https://trello.com/c/T1cqc3zg/27-view-only-access-to-postings-without-registration | As a visitor, I want to view postings on the platform without creating an account, such that I can explore available accommodations before deciding to register for additional features. | Not Groomed | P3 Future Sprint (purple) | 3
66fee56380d431355c8d2c31 | Query User List | https://trello.com/c/9X3VNI8s/8-query-user-list | As a admin, I want to be able to search users and filter through them, such that it is easier for management and user searches. | Not Groomed | P3 Future Sprint (purple) | 4 | query_user_list.feature
6705375021f3cb5addc6e131 | Rate Users | https://trello.com/c/Riew9dll/43-rate-users | As a user, I want to rate other users after interacting with them (e.g., after exchanging messages), so that I can provide feedback on my experience and help others make informed decisions. | Not Groomed | P3 Future Sprint (purple) | 5
670534edb97bdc1edf9b72a6 | Save Search Filters for Future Searches | https://trello.com/c/Uq6XHCFw/40-save-search-filters-for-future-searches | As a user, I want to save my recent search filters, so that I can easily reapply them when conducting future searches for accommodation listings that meet my preferences. | Not Groomed | P3 Future Sprint (purple) | 4
6702b5194f27ad768af42ede | Remember User when Logging in | https://trello.com/c/7cHKS5zu/39-remember-user-when-logging-in | As a user, I want to see a ‚ÄúRemember Me‚Äù checkbox on the login form, such that I can stay logged in for future sessions without re-entering my credentials | Not Groomed | P3 Future Sprint (purple) | 3
67022858f7987e1e0e9fbebe | Select Duration of Post Visibility | https://trello.com/c/vPoc7MKJ/38-select-duration-of-post-visibility | As a user, I want to be able to set an expiry date for my post. | Not Groomed | P3 Future Sprint (purple) | 4
6702249c2669cdeccf400910 | The Website Adapts to Screen Size | https://trello.com/c/icRUlgwg/36-the-website-adapts-to-screen-size | As a user, I want to be able to use the application on any screen size. | Not Groomed | P2 Next Sprint (orange) | 1
670223c7097752aef028e9db | The Distance Between the Listing Address and Campus is Displayed | https://trello.com/c/EbdQNlv7/35-the-distance-between-the-listing-address-and-campus-is-displayed | As a user, I want to see how far away each apartment is from the campus. | Not Groomed | P3 Future Sprint (purple) | 3
6702222a21415b9133b04a49 | Posts Displayed on Multiple Pages | https://trello.com/c/IwdaBMzG/34-posts-displayed-on-multiple-pages | As a user, I want to see the posts in a page with up to 20 posts, with the possibility of changing page. The post would be ordered by a selected filter. | Not Groomed | P3 Future Sprint (purple) | 3
6701dac202b939b8f821fa2c | Remove Subletting Posting | https://trello.com/c/RddUmNDn/32-remove-subletting-posting | As a Student User, I can delete a subletting posting, such that I won‚Äôt deal with requests after the total number of roommates has been found | Not Groomed | P3 Future Sprint (purple) | 2
6701ce862734a708aff80a44 | Update Subletting Posting | https://trello.com/c/FPv3cS4o/31-update-subletting-posting | As a Student User account, I want to update any fields of my subletting posting, such that I can modify any information in case circumstances change | Not Groomed | P3 Future Sprint (purple) | 1
6701b80c6809492df45a3d6d | Search Functionality | https://trello.com/c/vl3FLfog/30-search-functionality | As a user, I want to conduct a filtered search on the platform, such that I can view available accommodation listings that fit my needs as a tenant before deciding to contact the user who posted the ad. | Not Groomed | P2 Next Sprint (orange) | 4
6701b19d35f2af6f0fca1daa | Create Subletting Postings | https://trello.com/c/8DDGhXJ9/29-create-subletting-postings | As a Student User, I want to create a posting that references an existing landlord‚Äôs appartment listing, such that renters can look for roommates | Not Groomed | P3 Future Sprint (purple) | 3
670002a9594d1e66d7e9c951 | Filter for Apartments Based on a Score System | https://trello.com/c/avx14e4w/25-filter-for-apartments-based-on-a-score-system | As a user, I want to see a home page with a filter system based on filter criteria for each apartment located in a range around the set point and sorted based on a formula based on a weighted amount based on said filter criteria | Not Groomed | P3 Future Sprint (purple) | 1
66fefe3732ad09e9b21af698 | English/French toggle | https://trello.com/c/O2b7SoBM/23-english-french-toggle | As a customer, I want to read the content in my language of preference (English or French) so that I can easily understand the description of each posting. | Not Groomed | P3 Future Sprint (purple) | 4
66fefb96a2541dd9ca19e009 | Map Functionality | https://trello.com/c/5L23X9dZ/22-map-functionality | As a customer, I want to look for postings by location in a map so that I can easily find options close to my desired location. | Not Groomed | P3 Future Sprint (purple) | 4
66fefa339f4c6feed1dafa2b | Game to play when there is a 404 error | https://trello.com/c/gNKxa9N8/21-game-to-play-when-there-is-a-404-error | As a customer, I want to play a simple game when there is a 404 error so that I can release some stress and improve my overall experience with the website. | Not Groomed | P4 Future Sprint (blue) | 2
66fef839fd5a6a9f25c67a0e | Flag posts as scam | https://trello.com/c/uFWYok6y/20-flag-posts-as-scam | As a customer, I want to flag a suspicious post as scam so that the admin can review and remove the posting if necessary. | Not Groomed | P3 Future Sprint (purple) | 5
66fef670cdd653f71ee0866b | View Saved Posts | https://trello.com/c/WLX4nECw/19-view-saved-posts | As a user, I should be able to see my saved post with an indicator that shows whether I have sent the landlord a message | Not Groomed | P3 Future Sprint (purple) | 3
66fef66b49b006d4bc2a2233 | Like or Save a Post | https://trello.com/c/K3ELWXIo/18-like-or-save-a-post | As a user, I should be able to save a post such that they then appear in my saved posts | Not Groomed | P3 Future Sprint (purple) | 1
66fef5fb22f33ac1599ba182 | Save draft of your post | https://trello.com/c/Xxy2NDAE/17-save-draft-of-your-post | As a customer, I want to save a draft of my post so that I can leave the website and continue working on it when I come back. | Not Groomed | P3 Future Sprint (purple) | 5
66fef597b7aaa550eea2b66e | User Account Menu | https://trello.com/c/xzfIxlhQ/16-user-account-menu | As a user, I should have a menu for users to manage my account, on the same page where I can update my user info. Also, my user account should be visible to other users where they can see listings, ratings, etc., but in a view-only configuration. | Not Groomed | P2 Next Sprint (orange) | 4
66fef566c7601684a5f4ab16 | Landlord Account Verification | https://trello.com/c/nCQ6leS8/15-landlord-account-verification | As an admin, I want to be able to approve a landlord account, such that it can create postings. | Not Groomed | P2 Next Sprint (orange) | 5
66fef54e29d7a410fdbd3ad4 | Admin Menu | https://trello.com/c/oUOEIMMT/14-admin-menu | As an admin, I should have access to an admin menu, such that I can manage users, accounts, and postings. | Not Groomed | P2 Next Sprint (orange) | 5
66fef2b13603e30d6503e258 | Deactivate Account | https://trello.com/c/yAA50EGE/13-deactivate-account | NICE TO HAVE As a user, I want to be able to deactivate my account such that all my interactions with the website are hidden (listings, ratings, etc.) | Not Groomed | P4 Future Sprint (blue) | 3
66fef2897a0d12fe7ebb3717 | Complete (Rent Out) a Listing | https://trello.com/c/k79SuBK2/12-complete-rent-out-a-listing | As a user, I should be able to ‚Äúclose‚Äú a listing, so that it still appears in my account as ‚Äúsold‚Äú or ‚Äúrented‚Äú with the price, description, and everything, and such that other users can still see a my closed posts | Not Groomed | P2 Next Sprint (orange) | 3
66fef281a932327d13abaef6 | Delete a Listing | https://trello.com/c/0AZd3w2t/11-delete-a-listing | As a user, I want to be able to delete a posting that I posted, such that it can not be seen by me or by other users. | Not Groomed | P2 Next Sprint (orange) | 1
66fee53468e201c1681be00e | Secure User Authentication | https://trello.com/c/hww38oVc/7-secure-user-authentication | As a user, I want to have my data secured, such that it ensures the safety and privacy of my data. | Not Groomed | P2 Next Sprint (orange) | 9
66fee21db614b30627b34d34 | Roommate Matching System | https://trello.com/c/SJnrtkOQ/5-roommate-matching-system | As a user, I want to see recommended potential roomates based on compatibility in living preferences, such that i can message them. | Not Groomed | P3 Future Sprint (purple) | 4
66fee1a9c2d6476831a2f578 | Search and Filter Functionality | https://trello.com/c/qXw8Nefs/4-search-and-filter-functionality | As a user, I want to be able to search through postings, such that i can filter the postings that I see. | Not Groomed | P3 Future Sprint (purple) | 3
66fc379dd28db90a1c253771 | Password Reset Functionality | https://trello.com/c/mgHivFx0/1-password-reset-functionality | As a customer, I want to reset my password to access my account if I forget my login information. | Not Groomed | P2 Next Sprint (orange) | 5
67054e4a64fdfb611de083b5 | Mailing list to notify users of new postings | https://trello.com/c/7UY5wJ22/44-mailing-list-to-notify-users-of-new-postings | As a customer, I want to subscribe to a mailing list so that I get notified via email when new postings matching my preferences are available. | Not Groomed | P4 Future Sprint (blue) | 3
67058319c9351a2f62ab5525 | Mobile Site | https://trello.com/c/6q0lfEQ0/45-mobile-site | As a user, I want to be able to access the application on my mobile device. | Not Groomed | P4 Future Sprint (blue) | 1
6705840a4a894794e570d246 | View a sorted list of own listing | https://trello.com/c/X4djWyB1/46-view-a-sorted-list-of-own-listing | As a logged-in user, I want to be able to view all of my ads based on their current state (available, pending, closed, or unavailable) or other criteria of my choosing | Not Groomed | P3 Future Sprint (purple) | 1
67058d0dbe2b446b17f045e7 | Create an UI for Web page | https://trello.com/c/o2XCuNko/52-create-an-ui-for-web-page | Set up the UI for the pages people will be interacting with (create account page, log-in page, etc) | Not Groomed | P2 Next Sprint (orange) | 3